St. Michael’s Road Public Art Project Time Frame

1. Tuesday 22nd October Publish Project Brief

On www.longfordcoco.ie – mail-shot to existing sculptor database – send advertisement to Visual Artists Ireland www.visualartists.ie/contact/eguidelines

2.  Friday 1st November & Tuesday 5th November 12.00pm

Artist’s site visits with Arts Officer and Town Engineer

3. Tuesday 10th December 1.00pm Closing date for Submissions

4. Friday 10th January 2014 11.00 am Artistic Features Committee Adjudication Meeting

Committee members: Fiona Cormican Cluid rep. Mayor Longford Town Council Peggy Nolan, Town Engineer Brian McNeela, Paul Devine residents rep. County Arts Officer Fergus Kennedy, Dan Rooney Town Clerk, Frank Horne Comm. & Entps. Officer, Gary Robinson Visual Artist, Shelley Corcoran Visual Artist

5. Friday January 17th Notification of successful artist, arrangements to sign contracts and payment of first tranche of commission

6. Installation Friday 20th  June 2014